Rozana Resorts — Go-Live Roadmap

Resort PC installation · Biometric enrolment · Ops web app · Daily WhatsApp report

Prepared for: Rozana Resorts (Ooty Skyview go-live)
June 2026

# 1. What you are installing

Rozana is three connected pieces on one Supabase cloud database. This roadmap assumes development is complete and covers resort-side installation only.

| Component | Where it runs | Purpose |
| --- | --- | --- |
| Rozana Ops (web app) | Browser on any PC/phone | Manager & owner: attendance, HK, leave, reports |
| Attendance kiosk (Windows) | Dedicated PC at front desk | Staff punch IN/OUT with fingerprint |
| WhatsApp EOD sender (Baileys) | Office PC or small VPS (always on) | Daily report to owner at 6 PM IST |
| Supabase (cloud) | Already live | Database, photos, Edge Functions — no install at resort |

# 2. Before you travel to the resort

## 2.1 Hardware checklist

| Item | Specification | Notes |
| --- | --- | --- |
| Resort kiosk PC | Windows 10/11, 8 GB RAM, SSD | Always on; disable sleep |
| USB fingerprint reader | Mantra / SecuGen / Morpho with Windows SDK | Must support 1:N identify + enrolment |
| UPS | Recommended | Prevents corrupt punches during power cut |
| Stable internet | Wi‑Fi or Ethernet | Kiosk queues punches offline if dropped |
| Dedicated WhatsApp SIM (optional) | For EOD reports only | Linked via QR to Baileys sender PC |

## 2.2 Accounts & credentials to collect

Supabase project URL and anon key (same as Rozana Ops .env.local)

Supabase service_role key (Baileys sender only — keep secret)

Owner WhatsApp number (international digits, e.g. 9198XXXXXXXX)

Operations manager login (created in Rozana Ops)

Kiosk ADMIN_PIN (change from default 1234 before go-live)

## 2.3 Software to copy to a USB stick

Flutter Windows release build: rozana_attendance_kiosk.exe + .env

Fingerprint reader Windows drivers + SDK installer from vendor

Node.js 18+ installer (for WhatsApp sender PC, if separate)

Folder: Rozanaretreats/whatsapp-baileys (with .env configured)

This document

# 3. Day 1 — Cloud database (one-time)

Do this once in Supabase Dashboard (project oqksrcruypdmsggorrge) or confirm already done:

SQL Editor → run rozana_attendance_kiosk/supabase/kiosk_migrations.sql

Confirm tables: attendance_punches, fingerprint_templates, report_send_log

Confirm Realtime on attendance_punches (see kiosk_migrations.sql bottom)

Add all staff in Rozana Ops → Attendance → Add staff (with HK logins if needed)

Add rooms / HK tasks for the property

# 4. Day 2 — Install Rozana Ops (web app)

## 4.1 Production hosting (recommended)

Deploy Rozanaretreats/app to Netlify, Vercel, or similar

Set environment variables: VITE_SUPABASE_URL, VITE_SUPABASE_ANON_KEY

Set VITE_ALLOW_MANUAL_PUNCHES=false when kiosks are live

Managers open the URL in Chrome — bookmark on their phones

## 4.2 Local testing at resort (temporary)

Install Node.js on a laptop

Copy Rozanaretreats/app folder

Create .env.local with Supabase URL + anon key

Run: npm install && npm run dev

Open http://localhost:5173 — login as Firoz (manager) or Ruheed (owner)

# 5. Day 3 — Install fingerprint reader on resort PC

Install Windows updates; create dedicated Windows user (e.g. RozanaKiosk)

Install vendor USB fingerprint driver + SDK

Plug reader into USB; confirm device appears in Device Manager

Disable sleep: Settings → System → Power → Never sleep when plugged in

Set auto-login for RozanaKiosk user (optional, for 24/7 kiosk)

Important: Until the Windows native plugin is wired to your exact reader SDK, you can run mock mode for training. For live fingerprints set FINGERPRINT_READER=native after SDK integration is complete.

# 6. Day 4 — Install attendance kiosk app

## 6.1 Build release on dev machine

cd rozana_attendance_kiosk

flutter build windows

Output: build/windows/x64/runner/Release/

Copy entire Release folder to resort PC, e.g. C:/Rozana/Kiosk/

## 6.2 Configure .env on resort PC

Create C:/Rozana/Kiosk/.env with:

SUPABASE_URL=https://oqksrcruypdmsggorrge.supabase.co
SUPABASE_ANON_KEY=<your anon key>
PROPERTY_ID=ooty-skyview
DEVICE_ID=kiosk-ooty-pc-01
ADMIN_PIN=<choose 4–6 digits>
FINGERPRINT_READER=native
PUNCH_DEBOUNCE_SECONDS=30
MIN_MATCH_SCORE=60

## 6.3 Auto-start at Windows logon

Open Task Scheduler → Create Task

Trigger: At log on (RozanaKiosk user)

Action: Start program → C:/Rozana/Kiosk/rozana_attendance_kiosk.exe

Start in: C:/Rozana/Kiosk/

Reboot PC and confirm kiosk opens full screen automatically

# 7. Biometric enrolment — step by step

Fingerprints are enrolled on the kiosk only. Rozana Ops does not store templates. Each staff member is enrolled once before they can punch.

## 7.1 Who does what

| Role | Action |
| --- | --- |
| Operations manager (Firoz) | Opens Admin on kiosk; enrols each staff fingerprint |
| HK staff | Only places finger on idle screen — no login |
| Owner (Ruheed) | Views attendance in Rozana Ops — does not enrol |

## 7.2 Enrol one staff member

Confirm staff exists in Rozana Ops (Attendance → staff list) for this property

On kiosk idle screen, tap bottom label “Rozana Kiosk · device-id” five times quickly

OR tap Admin button (visible in mock/desktop mode)

Enter ADMIN_PIN from .env

Select staff name from dropdown

Tap “Capture fingerprint” — staff places finger on reader when prompted

Wait for green “Enrolled successfully” message

Repeat for each staff member (Arun, Vijay, Janaki, etc.)

## 7.3 Re-enrol or replace fingerprint

Same Admin flow — if already enrolled, app warns and allows capture again to replace

Use after reader swap, poor quality scan, or staff finger injury

## 7.4 Test punch after enrolment

Return to kiosk home (back from Admin)

Staff places finger on reader

First punch of the day → CHECKED IN (green banner)

Second punch → CHECKED OUT

Open Rozana Ops → Attendance — punch appears within 1–2 seconds (Kiosk badge)

# 8. Daily operations (after go-live)

| Time | What happens |
| --- | --- |
| All day | Staff punch IN/OUT at kiosk; manager uses Ops for HK & leave |
| Real-time | Ops Attendance updates live via Supabase |
| 6:00 PM IST | Baileys sends EOD WhatsApp report to owner |
| Anytime | Owner logs into Ops → Reports / Housekeeping for proof photos |

# 9. WhatsApp daily report (Baileys)

On always-on PC: cd Rozanaretreats/whatsapp-baileys

Edit .env: OWNER_WHATSAPP_NUMBERS, SUPABASE_ANON_KEY, EOD_CRON=0 18 * * *

Run start.cmd → scan QR once with sender phone (Linked devices)

Test: send-now.cmd

Leave start.cmd running; cron sends daily automatically

Owner views proof photos in Ops — WhatsApp message has no photo links

# 10. Go-live checklist

☐ kiosk_migrations.sql applied on Supabase

☐ All staff added in Rozana Ops

☐ Fingerprint reader drivers installed on resort PC

☐ Kiosk .env configured (PROPERTY_ID, DEVICE_ID, ADMIN_PIN)

☐ Every staff member fingerprint enrolled

☐ Test IN + OUT punch; visible in Ops Attendance

☐ VITE_ALLOW_MANUAL_PUNCHES=false in production Ops

☐ Baileys connected; test EOD received on owner number

☐ Task Scheduler auto-starts kiosk on boot

☐ Manager trained: Admin PIN, enrolment, Ops HK workflow

# 11. Troubleshooting

| Problem | Fix |
| --- | --- |
| Kiosk says “Finger not recognized” | Re-enrol in Admin; check reader cable |
| Punches not in Ops | Check internet; verify Supabase URL in .env |
| Ops shows old data | Hard refresh; check Supabase connection |
| WhatsApp not sent | Is start.cmd running? Run send-now.cmd to test |
| QR expired (Baileys) | Restart start.cmd; scan new QR |
| PC rebooted — kiosk not open | Check Task Scheduler path to .exe |

# 12. Support contacts & repo

GitHub: https://github.com/Rozanaretreats/Rozana-retreats

Supabase project: oqksrcruypdmsggorrge

Kiosk docs: rozana_attendance_kiosk/docs/PC_KIOSK_DEPLOYMENT.md

When reader model is known: share brand + SDK link for Windows plugin completion

— End of Rozana Go-Live Roadmap —